## High Level Road Map
| Envisioned GovStack Activities | [9 empty] | 09 June 2022 | 16 June 2022 | 23 June 2022 | 30 June 2022 | 7 July 2022 | 14 July 2022 | 21 July 2022
GovStack Country Engagement Framework Stage | Indicator | Activity ID | Activities | Description | Deliverable | Lead Organization | Timeline | Required Resources | Technical team composition will be adjusted based on 5 govt selection and BB to be implemented | Comments | UPDATES
Scoping | OI 1.1 | 1.1.1 | [5 empty] | Staff
| OI 1.1 | 1.1.2
Scoping | OI 1.1 | 1.1.3 | [5 empty] | Grant | The total implementation team is compose of: Project Lead HoA Regional Project Officer Expert Support (500 Consultancy days for all actions)
European Union delegation meetings - Map the stakeholders. CIO focal points in each countries Fill the Shared Holder Mapping
Scoping | OI 1.1 | 1.1.4 | [5 empty] | Grant
Scoping | OI 1.1 | 1.1.5 | [5 empty] | Grant | Project Lead HoA Regional Project Officer Expert Support (500 Consultancy days for all actions)
| OI 1.1 | 1.1.6 | [5 empty] | Grant
| OI 1.2 | 1.2.1 | [5 empty] | Grant
| OI 1.2 | 1.2.2 | [5 empty] | staff
| OI 2.1 | 1.2.0. | [5 empty] | Grant | Project Lead HoA Regional Project Officer Expert Support (500 Consultancy days for all actions)
| OI 2.1 | 2.1.1 | [5 empty] | Grant | Project Lead HoA Regional Project Officer Expert Support (500 Consultancy days for all actions)
| OI 2.1 | 2.1.2 | [5 empty] | Grant
| OI 2.1 | 2.1.3 | [5 empty] | Grant
| OI 2.1 | 2.1.4 | [5 empty] | Grant | Project Lead HoA Regional Project Officer Expert Support (500 Consultancy days for all actions)
| OI 2.2 | 2.2.1 | [5 empty] | staff/service contract
| OI 2.2 | 2.2.2 | [5 empty] | staff/service contract
| OI 2.2 | 2.2.3 | [5 empty] | staff/service contract
| OI 2.2 | 2.2.4 | [5 empty] | service contract |  | This is not forseen at this point.
| OI 2.2 | 2.2.5 | [5 empty] | Grant | Project Lead HoA Regional Project Officer Expert Support (500 Consultancy days for all actions)
| OI 2.2 | 2.2.6 | [5 empty] | Grant
| OI 3.1 | 3.1.1 | 3 concepts for technical training modules related to the e-government building blocks are identified | DIAL will evaluate the existing gaps within government IT practitioners in terms of knowledge, skills, strengths, weaknesses, opportunities, threats, assets and other elements required for them to achieve the pre-specified objectives. Three (3) steps are involved in the capacity needs assessment. The first step will involve identifying the existing capacity amongst government IT. At this stage, existing assets, SWOT analysis, existing knowledge and skills and existing policy environment will be identified. The second step involves identification of the desired levels of capacity. This is the capacity level necessary for the objectives to be achieved. A consideration will be given to the government IT practitioners' ability to achieve this capacity. Finally, the gap between the two steps is identified which is the difference between the desired and the existing levels of capacity. | Review Sierra Leone approach: (DP, global certifications, building blocks, catalog, PMU, leadership development, MEL) Familiarize with complementary GovStack initiatives and learning resources: (Digital Government primer, situational analysis, vision, best practices, planning, Gov Enterprise Architecture, Building Blocks, Interoperability) Capacity building needs assessment (gap analysis) Support relevant stakeholder mapping led by GIZ and countries High-level concept note / PPT (one per country). Findings and recommendations: Action plan Monitoring, evaluation, and learning (MEL) plan Selected stakeholders and engagement map Change management plan Communities of practice (working groups) Prioritize user personas Preliminary curriculum/learning journey (per selected user persona) Communications plan Set up program management unit | DIAL | (TBD on proposal dev.) | Grant
| OI 3.1 | 3.1.2 | 3 technical training modules are developed | Following the determination of the gaps between desired and existing capacity, DIAL will develop and customize a set of training modules ranging from generic foundational modules such as the Principles for Digital Development to specialist ICT frameworks: Service Management (ITIL), Project Management (PRINCE2), Change Management and Agile, IT Governance (COBIT) and Enterprise Architecture (TOGAF). This sub activity includes establishing partnerships with accrediting organizations e.g. OpenGroup, Axelos and ISACA. Out of earlier needs assessment in HOAI engagement by partners and capacity needs review, DIAL will further structure the needed Building Blocks topics into a streamline curriculum so it is staged at the appropriate moments in the engagement process to complement use case and building block identification, and design and implementation activities underway in parallel. As building block priorities become apparent, DIAL and partners with country input will review and vet the list of technical topics required and the desired approach for delivery. This will set the baseline for S.A. 2.2. | Prepare Scope of Work (potential outsourced activities): Landscape assessment (building blocks) Enterprise architecture Capacity building (refine curriculum, instructional design, case studies, pre and post assessments, etc.) Other (from high concept note) Refine action plan, include building block selection Calendar: Request for proposals and partner(s) selection Review and development narrative and needs on core knowledge areas per building block and digital government infrastructure in general as technical topics Set up SoW and source knowledge partner to develop a landscape of relevant / applicable training components by-supply, formats, and entities (based on geographies and specialties) Assess Kenya’s network of trainer's capacity (ongoing by DIAL) and alignment to HoAI Assess approaches to harmonize these structured topics / material and framework to activate existing training entities for HoAI context and for global GovStack reuse Derive curriculum and execute on training delivery on prioritized topics (as identified from initial scoping and needs assessments) Prioritized building block topics as defined by needs assessments and earlier-stage scoping, design, use case identification and implementation activities of the HoAI engagement Landscape of relevant training modules, materials, and suppliers Training modules and timing / logistics and country feedback | DIAL | (TBD on proposal dev.) | Grant
| OI 3.1 | 3.1.3 | 9 Technical trainings are carried out | The course modules and certifications would be delivered using a blended learning and bootcamp approach to the selected participants (IT practitioners leading and implementing key information systems) from government. In order to ensure effective transfer of practical knowledge and the participants understanding and application of the frameworks, the training will make extensive use of presentations, practical examples, experience sharing, role play and discussions. At the end of each module, the participants would be required to take the international certification exam. | Prepare Scope of Work (potential outsourced activities): Landscape assessment (building blocks) Enterprise architecture Capacity building (refine curriculum, instructional design, case studies, pre and post assessments, etc.) Other (from high concept note) Refine action plan, include building block selection Calendar: Request for proposals and partner(s) selection | DIAL | (TBD on proposal dev.) | Grant
| OI 3.1 | 3.1.4 | Feedback mechanisms/surveys for the training modules are developed and shared with participants | Network management Kick-off meeting Recurrent updates Closing meeting | Calendar of events Branding guidelines Agenda templates Program report template Final report template | DIAL | (TBD on proposal dev.) | Grant
| OI 3.1 | 3.1.5 | Feedback on trainings is analyzed | (same as above) | (same as above) | DIAL | (TBD on proposal dev.) | Grant
| OI 3.3 | 3.3.1 | Identification and hosting of 4 communities of practice for GovStack in the region | (Similar to below) | (Similar to below) | DIAL | (TBD on proposal dev.) | Grant
| OI 3.3 | 3.3.2 | A regional digital government leaders forum is set-up and once a year | DIAL and Smart Africa are supporting a Digital Econonmy working group. chaired by Kenya with high level government representatives. DIAL also convening in country donor roundtable to explore how donors complement current activities in digital-gov.ernment. Extract process or experiences from Sierra Leone to the other countries. to convene in-country donor meetings | Using the information generated during the comprehensive landscape, DIAL and HoAI partners may suggest integration into the Africa Data Leadership Initiative (ADLI), an active peer network designed for and by African policymakers, consumer rights advocates, and private sector stakeholders. ADLI is a forum for African thinker-doers to ensure the data economy drives equitable growth and social progress across the continent. In addition to specialized communities of practices to include communities composed of technical personnel and implementing team members. An example is The Open Group Architecture Forum and Government EA Work Group, which provides a vendor-neutral environment to learn about and develop EA standards that align with business / government objectives and deliver greater value. | DIAL | (TBD on proposal dev.) | Grant
|  |  | Additional Capacity Development | DIAL will engage with a knowledge partner via tender to lead in drawing a comprehensive landscape of supply-side entities, modules, and materials current in-market that can meet the needs of the identified building block areas. This will help create a detailed snapshot and mapping of whom has right set of specialties and knowledge areas to deliver on certain topics, via what format and within which geographies. This can both be used in identifying thereafter relevant training partners to work with, within the HOAI context, but also as a one-time resource to GovStack to inform / address capacity development needs in general across country engagements. The knowledge partner can further help GovStack partnerships on elevating the potential concept of framework agreements in activating relevant training delivery entities in addressing capacity requirements both within HoAI and in other country assistances. | Landscape of relevant training modules, materials, and suppliers | DIAL |  | Grant
| Additional Activites on a global level to support via EU BUdget |  | Digital Government Forum, Capacity Development (Trainings, Material, e-learning, communication) + Communities of Practices, Peer-Learning, Development of Catalog / Matching BB with Specifications | (est. based on GIZ direction: some of what is described at global level will be within this amount) | (same as above) | DIAL | (TBD on proposal dev.) | Grant
|  | Suggestion | Pilot defined use cases in country infraestructure at small scale | Use the MVP and Pilot in real context |  |  | Dec 2024